## Summary
BSTI 2.0 – Revised financial structure (work-volume based, ≤ 2 crore per approval)
Prepared 19 Oct 2026. Basis: OrangeBD Financial Proposal V4 (Sep 2026), BSTI 2.0.pptx feature counts, BSTI priority list (serial.docx). Rollout total unchanged; amounts exclude VAT unless stated.
| Rollout total (unchanged) | 111665000
| Maintenance 2030–31 (unchanged) | 75240000
| Grand total (excl. VAT) | 186905000
| Number of approval packages (rollout) | 8
| Largest approval incl. VAT (crore) | 1.9972
| Last go-live deadline | 2029-12-31
Approval packages
Package | Scope | Value (BDT, excl. VAT) | Value incl. VAT (BDT) | Crore incl. VAT | Cap check | Work start | Go-live deadline
WP0 | Interim operation & maintenance of the 5 live services (Aug–Dec 2026), as proposed | 1625000 | 1868750 | 0.18688 | OK | 2026-08-01 | 2026-12-31
WP1 | BSTI 2.0 transformation: common platform, HRM & Leave, Payroll, Standards (BDS) sale; Accounts | 12379000 | 14235850 | 1.4236 | OK | 2027-01-01 | 2027-06-30
WP2 | CM licence services (non-scope & scope: new, renewal, brand inclusion) + common suspension / cancellation / withdrawal | 16120000 | 18538000 | 1.8538 | OK | 2027-03-01 | 2027-11-30
WP3 | Laboratory testing (Chemical, Physical, Energy Meter) and PCR services | 17063000 | 19622450 | 1.9622 | OK | 2027-02-01 | 2027-11-30
WP4 | Enforcement & field metrology: Mobile Court, Surveillance, Verification, Tank Calibration, Metrology Licence, Storage Tank Calibration | 17336000 | 19936400 | 1.9936 | OK | 2028-04-01 | 2028-12-31
WP5 | MSC services (issue, renewal, scope inclusion) | 16241000 | 18677150 | 1.8677 | OK | 2028-10-01 | 2029-06-30
WP6 | Halal certification, LPG / Fuel station registration, Case Management | 17367000 | 19972050 | 1.9972 | OK | 2029-01-01 | 2029-09-30
WP7 | I&S Metrology Calibration (NML), Building measurement, BSW API integration, Importer/Exporter certificates* | 13534000 | 15564100 | 1.5564 | OK | 2029-04-01 | 2029-12-31
| TOTAL ROLLOUT | 111665000 | 128414750 | 12.8415
Year-wise cash flow: revised vs proposal (BDT, excl. VAT)
Year |  | Proposal (as submitted) | Revised: rollout | Revised: maintenance | Revised: total | Difference, revised − proposal (lakh) | Revised incl. VAT
2026 |  | 1625000 | 1625000 | 0 | 1625000 | 0 | 1868750
2027 |  | 20520000 | 42243700 | 0 | 42243700 | 217.237 | 48580255
2028 |  | 39990000 | 22168900 | 0 | 22168900 | -178.211 | 25494235
2029 |  | 49530000 | 44274000 | 0 | 44274000 | -52.56 | 50915100
2030 |  | 37620000 | 1353400 | 37620000 | 38973400 | 13.534 | 44819410
2031 |  | 37620000 | 0 | 37620000 | 37620000 | 0 | 43263000
Total |  | 186905000 | 111665000 | 75240000 | 186905000 | 0 | 214940750
| Check: revised total equals proposal total | OK
Checks
| Milestone percentages total 100% | OK
| Work Volume allocation equals development pool | OK
| Package total equals rollout total | OK
| Every Work Volume row assigned to a package | OK
| All rollout packages within the 2-crore cap | OK
| Payment schedule reconciles to rollout and maintenance | OK
| Each maintenance tranche within the cap | OK
| Original offer recomputes to proposal totals | OK
| Accounts, CM, PCR and labs (WP1–WP3) live by the Dec 2027 deadline | OK

## Inputs
Inputs and assumptions
Blue = input you can change. Yellow = BSTI assumption to confirm. Black = formula.
Rollout total, OrangeBD Financial Proposal V4 (BDT, excl. VAT) | 111665000 | Source: Financial Proposal V4, p.4 (Aug 2026 – Dec 2029). Kept unchanged as instructed.
Interim O&M of 5 live services, Aug–Dec 2026 (BDT) | 1625000 | Source: Financial Proposal V4, p.4 (5 services × 65,000 × 5 months = 16,25,000). Kept as a separate O&M package, not development. Set to 0 to allocate the whole rollout by work volume.
Development pool allocated by work volume (BDT) | 110040000 | Formula
Maximum value per approval (BDT) | 20000000 | User instruction: at most 2 crore can be approved at a time.
VAT and taxes for the approval check | 15% | Assumption: 15% standard VAT. Proposal prices exclude VAT (p.3). Confirm the applicable VAT/AIT rate with Accounts; set to 0 if the 2-crore limit applies to the price excluding VAT.
Apply the cap to the value including VAT? (Y/N) | Y | Y = check package value incl. VAT against the cap (safer). N = check value excl. VAT.
Maintenance total 2030–2031 (BDT, excl. VAT) | 75240000 | Source: Financial Proposal V4, p.5 (33 × 95,000 × 24 = 7,52,40,000). Unchanged.
Maintenance period (months) | 24 | Jan 2030 – Dec 2031
Maintenance months per approval | 3 | Quarterly, matching the proposal's payment mode (p.3). 6 months fits the cap only if VAT is excluded from it.
Maintenance start | 2030-01-01 | Source: Financial Proposal V4, p.5
Round package values to (digits, -3 = nearest 1,000) | -3 | Last package absorbs the rounding so the total stays exactly equal to the rollout total.
Deadline: Accounts, CM, PCR and lab testing fully running | 2027-12-31 | User instruction (19 Oct 2026): lab testing cannot be delayed; CM + PCR + labs + Accounts must be fully running within December 2027. Applies to WP1–WP3.
Work-type weighting factor | Factor | Meaning
N | 1 | N = New build: first workflow of its family; full feature count counts as work.
V | 0.5 | V = Variant: renewal / brand inclusion / re-certification / scope inclusion of a family built in the same package. Session 1 found these SRS sections 85–99% identical text (difflib), so most of the work is configuration.
L | 0.5 | L = Live in v1: already running (HRM, Payroll, Standards sale, CM new, PCR new). Work is re-platforming into v2: 23-office organogram, SSO, shared engines and data migration.
Set every factor to 1.00 to allocate purely by the deck's feature counts.
Payment milestone (each development package) | % of package | Acceptance evidence
M1 Design & prototype sign-off | 20% | Package SRS detail (forms, fields, fee rules, desk roles, acceptance criteria) and clickable prototype approved by the wing.
M2 UAT acceptance | 30% | UAT signed by the wing focal point and ICT; zero open critical defects.
M3 Go-live | 40% | All services in the package live at HQ and the relevant regional offices with real transactions; data migrated; training done.
M4 End of stabilisation | 10% | Retention: released after the stabilisation period with SLA met; source code and documentation deposited.
Check: milestones total 100% | OK

## Work Volume
Work volume and cost allocation by priority (serial.docx order)
Volume = feature count per service from OrangeBD's BSTI 2.0.pptx (slides 14–46). Work units = features used × work-type factor. Each row's cost = its share of work units × development pool. Yellow = BSTI estimate where the SRS/deck gives no scope.
Priority | Serial ref | Service / module (as in serial.docx) | Package | Deck service | Deck service title | Modules (deck) | Features (deck, parent service) | Features used | Basis for features used | Work type (N/V/L) | Factor | Include? (Y/N) | Work units | Share of work | Allocated (BDT) | Allocated (lakh)
1 | 1 | BSTI 2.0 Transformation: common platform (unified portal & SSO, 23-office organogram, workflow / fee-payment / certificate-QR engines, v1 data migration) | WP1 | — | Not a separate deck service (shown in SRS architecture, p.17) |  |  | 60 | BSTI estimate: no feature list in SRS | N | 1 | Y | 60 | 3.317% | 3649751.2438 | 36.4975
1 | 1(i) | HRM & Leave | WP1 | S01 | HRM & Leave Management | 11 | 49 | 49 | Deck slide 14 | L | 0.5 | Y | 24.5 | 1.354% | 1490315.0912 | 14.9032
1 | 1(ii) | Payroll | WP1 | S02 | Payroll Management | 15 | 84 | 84 | Deck slide 15 | L | 0.5 | Y | 42 | 2.322% | 2554825.8706 | 25.5483
1 | 1(iii) | BDS sell (Standards sale) | WP1 | S23* | Replaces S23 slot; no scope in SRS or deck |  |  | 40 | BSTI estimate: move into portal/SSO, link to CM application, shared payment | L | 0.5 | Y | 20 | 1.106% | 1216583.7479 | 12.1658
2 | 2 | Accounts | WP1 | S03 | Finance & Accounts Management | 10 | 57 | 57 | Deck slide 16 | N | 1 | Y | 57 | 3.151% | 3467263.6816 | 34.6726
3 | 3(i) | CM Non-Scope Products (new licence) | WP2 | S05 | CM Mandatory New Certification | 12 | 46 | 46 | Deck slide 18 | L | 0.5 | Y | 23 | 1.271% | 1399071.3101 | 13.9907
3 | 3(ii) | CM Non-Scope Product Renewal | WP2 | S06 | CM Mandatory Renewal | 12 | 46 | 46 | Deck slide 19 | V | 0.5 | Y | 23 | 1.271% | 1399071.3101 | 13.9907
3 | 3(iii) | CM Non-Scope Brand Inclusion | WP2 | S07 | CM Mandatory Brand Inclusion | 12 | 46 | 46 | Deck slide 20 | V | 0.5 | Y | 23 | 1.271% | 1399071.3101 | 13.9907
3 | 3(iv) | CM Scope Product | WP2 | S08 | CM Scope New Certification | 16 | 83 | 83 | Deck slide 21 | N | 1 | Y | 83 | 4.588% | 5048822.5539 | 50.4882
3 | 3(v) | CM Scope Product Renewal | WP2 | S09 | CM Scope Renewal Certification | 16 | 83 | 83 | Deck slide 22 | V | 0.5 | Y | 41.5 | 2.294% | 2524411.2769 | 25.2441
3 | 3(vi) | CM Scope Brand Inclusion | WP2 | S10 | CM Scope Brand Inclusion | 16 | 83 | 83 | Deck slide 23 | V | 0.5 | Y | 41.5 | 2.294% | 2524411.2769 | 25.2441
3 | Footnote | All types of Suspension / Cancellation / Withdrawal of certificates and licences (common module, reused by every later package) | WP2 | — | Not in deck; MSC/CM gaps flagged by wings in 2025 |  |  | 30 | BSTI estimate | N | 1 | Y | 30 | 1.658% | 1824875.6219 | 18.2488
4 | 4 | Chemical Testing | WP3 | S14 | Chemical Testing | 20 | 67 | 67 | Deck slide 27 | N | 1 | Y | 67 | 3.704% | 4075555.5556 | 40.7556
5 | 5 | Physical Testing | WP3 | S15 | Physical Testing | 10 | 72 | 72 | Deck slide 28 | N | 1 | Y | 72 | 3.98% | 4379701.4925 | 43.797
6 | 6 | Energy Meter Testing | WP3 | S16 | Physical Lab – Energy Meter | 12 | 71 | 71 | Deck slide 29 | N | 1 | Y | 71 | 3.925% | 4318872.3051 | 43.1887
7 | 7(i) | PCR new | WP3 | S19 | PCR Registration New | 13 | 48 | 48 | Deck slide 32 | L | 0.5 | Y | 24 | 1.327% | 1459900.4975 | 14.599
7 | 7(ii) | PCR Renewal | WP3 | S20 | PCR Registration Renewal | 13 | 48 | 48 | Deck slide 33 | V | 0.5 | Y | 24 | 1.327% | 1459900.4975 | 14.599
7 | 7(iii) | PCR Brand Inclusion | WP3 | S21 | PCR Brand Inclusion | 13 | 45 | 45 | Deck slide 34 | V | 0.5 | Y | 22.5 | 1.244% | 1368656.7164 | 13.6866
8 | 8 | Mobile Court | WP4 | S33 | Mobile Court & Surveillance e-Service | 8 | 49 | 26 | Deck slide 46 modules: Mobile Court 18 + Product 5 + Tracking 3 | N | 1 | Y | 26 | 1.437% | 1581558.8723 | 15.8156
9 | 9(i) | Surveillance – Operational Activities | WP4 | S33 | Mobile Court & Surveillance e-Service | 8 | 49 | 11.5 | Deck slide 46: remaining 23 features (Surveillance 10, Sample 7, Test report 2, Admin 2, Workflow 2) split equally | N | 1 | Y | 11.5 | 0.6357% | 699535.6551 | 6.9954
9 | 9(ii) | Surveillance – List of Illegal Establishments | WP4 | S33 | Mobile Court & Surveillance e-Service | 8 | 49 | 11.5 | As above | N | 1 | Y | 11.5 | 0.6357% | 699535.6551 | 6.9954
10 | 10(i) | Verification – Petrol Pump | WP4 | S32 | Verification Service | 12 | 48 | 12 | Deck slide 45; split equally over 4 sub-types | N | 1 | Y | 12 | 0.6633% | 729950.2488 | 7.2995
10 | 10(ii) | Verification – Weighing Scale (general) | WP4 | S32 | Verification Service | 12 | 48 | 12 | As above | N | 1 | Y | 12 | 0.6633% | 729950.2488 | 7.2995
10 | 10(iii) | Verification – Weighing Scale (Association) | WP4 | S32 | Verification Service | 12 | 48 | 12 | As above | N | 1 | Y | 12 | 0.6633% | 729950.2488 | 7.2995
10 | 10(iv) | Verification – Weighbridge | WP4 | S32 | Verification Service | 12 | 48 | 12 | As above | N | 1 | Y | 12 | 0.6633% | 729950.2488 | 7.2995
11 | 11(i) | Tank Calibration – Tank Lorry | WP4 | S26 | Tank Lorry Calibration | 12 | 49 | 24.5 | Deck slide 39; split equally over 2 sub-types | N | 1 | Y | 24.5 | 1.354% | 1490315.0912 | 14.9032
11 | 11(ii) | Tank Calibration – Road-Tanker | WP4 | S26 | Tank Lorry Calibration | 12 | 49 | 24.5 | As above | N | 1 | Y | 24.5 | 1.354% | 1490315.0912 | 14.9032
12 | 12(i) | Metrology License New | WP4 | S24 | Metrology License Issue | 13 | 54 | 54 | Deck slide 37 | N | 1 | Y | 54 | 2.985% | 3284776.1194 | 32.8478
12 | 12(ii) | Metrology License Renewal | WP4 | S25 | Metrology License Renewal | 13 | 54 | 54 | Deck slide 38 | V | 0.5 | Y | 27 | 1.493% | 1642388.0597 | 16.4239
13 | 13(i) | Storage Tank Calibration – Underground | WP4 | S30 | Storage Tank Calibration | 13 | 58 | 11.6 | Deck slide 43; split equally over 5 sub-types | N | 1 | Y | 11.6 | 0.6412% | 705618.5738 | 7.0562
13 | 13(ii) | Storage Tank Calibration – Overhead | WP4 | S30 | Storage Tank Calibration | 13 | 58 | 11.6 | As above | N | 1 | Y | 11.6 | 0.6412% | 705618.5738 | 7.0562
13 | 13(iii) | Storage Tank Calibration – Oil-Tanker | WP4 | S30 | Storage Tank Calibration | 13 | 58 | 11.6 | As above | N | 1 | Y | 11.6 | 0.6412% | 705618.5738 | 7.0562
13 | 13(iv) | Storage Tank Calibration – Barge | WP4 | S30 | Storage Tank Calibration | 13 | 58 | 11.6 | As above | N | 1 | Y | 11.6 | 0.6412% | 705618.5738 | 7.0562
13 | 13(v) | Storage Tank Calibration – Lighter | WP4 | S30 | Storage Tank Calibration | 13 | 58 | 11.6 | As above | N | 1 | Y | 11.6 | 0.6412% | 705618.5738 | 7.0562
14 | 14(i) | MSC Issue | WP5 | S17 | MSC Certification | 24 | 174 | 174 | Deck slide 30 | N | 1 | Y | 174 | 9.619% | 10584278.607 | 105.8428
14 | 14(ii) | MSC Renewal | WP5 | S18 | MSC Re-certification | 14 | 136 | 136 | Deck slide 31 | V | 0.5 | Y | 68 | 3.759% | 4136384.743 | 41.3638
14 | 14(iii) | MSC Scope Inclusion | WP5 | — | Not in deck or SRS |  |  | 50 | BSTI estimate (similar to a brand / scope inclusion) | V | 0.5 | Y | 25 | 1.382% | 1520729.6849 | 15.2073
15 | 15(i) | Halal Certificate New | WP6 | S11 | CM Halal Certification | 16 | 86 | 86 | Deck slide 24 | N | 1 | Y | 86 | 4.754% | 5231310.1161 | 52.3131
15 | 15(ii) | Halal Recertification | WP6 | S12 | CM Halal Renewal Certification | 16 | 86 | 86 | Deck slide 25 | V | 0.5 | Y | 43 | 2.377% | 2615655.058 | 26.1566
15 | 15(iii) | Halal Brand Inclusion | WP6 | S13 | CM Halal Brand Inclusion | 16 | 86 | 86 | Deck slide 26 | V | 0.5 | Y | 43 | 2.377% | 2615655.058 | 26.1566
16 | 16(i) | LPG Bottling Plant / LPG Filling / Fuel Filling Station – New Registration | WP6 | S27 | LPG / Fuel Station Registration | 12 | 53 | 53 | Deck slide 40 | N | 1 | Y | 53 | 2.93% | 3223946.932 | 32.2395
16 | 16(ii) | LPG Bottling Plant / LPG Filling / Fuel Filling Station – Renewal | WP6 | S28 | LPG / Fuel Station Renewal | 12 | 53 | 53 | Deck slide 41 | V | 0.5 | Y | 26.5 | 1.465% | 1611973.466 | 16.1197
17 | 17 | Case Management | WP6 | S04 | Case Management System | 8 | 34 | 34 | Deck slide 17 | N | 1 | Y | 34 | 1.879% | 2068192.3715 | 20.6819
18 | 18 | I&S Metrology Calibration (NML) | WP7 | S31 | Industrial & Scientific Metrology Calibration | 14 | 59 | 59 | Deck slide 44 | N | 1 | Y | 59 | 3.261% | 3588922.0564 | 35.8892
19 | 19 | Building (flat) / Establishment Measurement | WP7 | S29 | Building / Establishment Measurement | 12 | 53 | 53 | Deck slide 42 | N | 1 | Y | 53 | 2.93% | 3223946.932 | 32.2395
20 | 20 | API integration with BSW (Bangladesh Single Window) | WP7 | — | Not in deck or SRS |  |  | 30 | BSTI estimate | N | 1 | Y | 30 | 1.658% | 1824875.6219 | 18.2488
21 | Footnote* | Registered Importer/Exporter Certificate Management | WP7 | S22 | Registered Importer/Exporter Certificate | 12 | 53 | 53 | Deck slide 35 (marked * in serial.docx) | N | 1 | Y | 53 | 2.93% | 3223946.932 | 32.2395
21 | Footnote* | Registered Importer/Exporter Certificate Management – Renewal | WP7 | S23 | Registered Importer/Exporter Renewal | 12 | 55 | 55 | Deck slide 36 (marked * in serial.docx) | V | 0.5 | Y | 27.5 | 1.52% | 1672802.6534 | 16.728
|  | TOTAL | [5 empty] | 2378 |  |  |  |  | 1809 | 100% | 110040000 | 1100.4
|  | Check: allocation equals development pool | [12 empty] | OK
|  | Implied cost per work unit (BDT) | [12 empty] | 60829.1874

## Packages
Approval packages (each ≤ 2 crore) and development time limits
Packages follow the serial.docx priority. Each is approved, contracted and paid separately. Schedule inputs (blue) are months; dates are calendar month-ends. Time limit = go-live deadline in the work order.
Package | Scope | Priorities (serial.docx) | Work units | Value by work share (BDT) | Package value (BDT, excl. VAT) | VAT & taxes (BDT) | Value incl. VAT (BDT) | Value incl. VAT (crore) | Within 2-crore cap? | Work start | Design (m) | Build (m) | UAT (m) | Go-live (m) | Stabilisation (m) | Time limit to go-live (months) | Approval needed by | M1 Design sign-off | M2 UAT acceptance | M3 Go-live deadline | M4 Stabilisation end | Services in package
WP0 | Interim operation & maintenance of the 5 live services (Aug–Dec 2026), as proposed | Live services | — | 1625000 | 1625000 | 243750 | 1868750 | 0.18688 | OK | 2026-08-01 | — | — | — | — | — | — | 2026-12-31 | — | — | 2026-12-31 | — | 5
WP1 | BSTI 2.0 transformation: common platform, HRM & Leave, Payroll, Standards (BDS) sale; Accounts | 1–2 | 203.5 | 12378739.6352 | 12379000 | 1856850 | 14235850 | 1.4236 | OK | 2027-01-01 | 1 | 3 | 1 | 1 | 3 | 6 | 2026-11-30 | 2027-01-31 | 2027-05-31 | 2027-06-30 | 2027-09-30 | 5
WP2 | CM licence services (non-scope & scope: new, renewal, brand inclusion) + common suspension / cancellation / withdrawal | 3 | 265 | 16119734.66 | 16120000 | 2418000 | 18538000 | 1.8538 | OK | 2027-03-01 | 2 | 5 | 1 | 1 | 3 | 9 | 2027-01-31 | 2027-04-30 | 2027-10-31 | 2027-11-30 | 2028-02-29 | 7
WP3 | Laboratory testing (Chemical, Physical, Energy Meter) and PCR services | 4–7 | 280.5 | 17062587.0647 | 17063000 | 2559450 | 19622450 | 1.9622 | OK | 2027-02-01 | 2 | 6 | 1 | 1 | 3 | 10 | 2026-12-31 | 2027-03-31 | 2027-10-31 | 2027-11-30 | 2028-02-29 | 6
WP4 | Enforcement & field metrology: Mobile Court, Surveillance, Verification, Tank Calibration, Metrology Licence, Storage Tank Calibration | 8–13 | 285 | 17336318.408 | 17336000 | 2600400 | 19936400 | 1.9936 | OK | 2028-04-01 | 2 | 5 | 1 | 1 | 3 | 9 | 2028-02-29 | 2028-05-31 | 2028-11-30 | 2028-12-31 | 2029-03-31 | 16
WP5 | MSC services (issue, renewal, scope inclusion) | 14 | 267 | 16241393.0348 | 16241000 | 2436150 | 18677150 | 1.8677 | OK | 2028-10-01 | 2 | 5 | 1 | 1 | 3 | 9 | 2028-08-31 | 2028-11-30 | 2029-05-31 | 2029-06-30 | 2029-09-30 | 3
WP6 | Halal certification, LPG / Fuel station registration, Case Management | 15–17 | 285.5 | 17366733.0017 | 17367000 | 2605050 | 19972050 | 1.9972 | OK | 2029-01-01 | 2 | 5 | 1 | 1 | 3 | 9 | 2028-11-30 | 2029-02-28 | 2029-08-31 | 2029-09-30 | 2029-12-31 | 6
WP7 | I&S Metrology Calibration (NML), Building measurement, BSW API integration, Importer/Exporter certificates* | 18–21 | 222.5 | 13534494.1957 | 13534000 | 2030100 | 15564100 | 1.5564 | OK | 2029-04-01 | 2 | 5 | 1 | 1 | 3 | 9 | 2029-02-28 | 2029-05-31 | 2029-11-30 | 2029-12-31 | 2030-03-31 | 5
| TOTAL ROLLOUT |  | 1809 | 111665000 | 111665000 | 16749750 | 128414750 | 12.8415 | [11 empty] | 2029-12-31 |  | 53
| Check: package total equals rollout total in the proposal |  |  |  | OK
| Check: every included Work Volume row is assigned to a package |  |  |  | OK
| Largest single approval (crore, incl. VAT) |  |  |  | 1.9972
| Overall development time limit: from first work start to last go-live (months) |  |  |  | 36
Formulas:
Approval needed by = EOMONTH([Work start],-2)
M1 Design sign-off = EOMONTH([Work start],[Design (m)]-1)
M2 UAT acceptance = EOMONTH([Work start],[Design (m)]+[Build (m)]+[UAT (m)]-1)
M3 Go-live deadline = EOMONTH([Work start],[Time limit to go-live (months)]-1)
M3 Go-live deadline = MAX(U5:[M3 Go-live deadline, row above])
M4 Stabilisation end = EOMONTH([Work start],[Time limit to go-live (months)]+[Stabilisation (m)]-1)
Note on F12: Balancing figure: takes the rounding of the other packages so the rollout total stays exactly 11,16,65,000.

## Payment Schedule
Milestone payment schedule
Payment only on accepted milestones (see Inputs for acceptance evidence). Maintenance is unchanged from the proposal and approved in quarterly tranches.
Phase | Package | Milestone | % of package | Due by | Year | Amount (BDT, excl. VAT) | VAT & taxes (BDT) | Amount incl. VAT (BDT)
Rollout | WP0 | Interim O&M lump sum, Aug–Dec 2026 | 100% | 2026-12-31 | 2026 | 1625000 | 243750 | 1868750
Rollout | WP1 | M1 Design & prototype sign-off | 20% | 2027-01-31 | 2027 | 2475800 | 371370 | 2847170
Rollout | WP1 | M2 UAT acceptance | 30% | 2027-05-31 | 2027 | 3713700 | 557055 | 4270755
Rollout | WP1 | M3 Go-live | 40% | 2027-06-30 | 2027 | 4951600 | 742740 | 5694340
Rollout | WP1 | M4 End of stabilisation | 10% | 2027-09-30 | 2027 | 1237900 | 185685 | 1423585
Rollout | WP2 | M1 Design & prototype sign-off | 20% | 2027-04-30 | 2027 | 3224000 | 483600 | 3707600
Rollout | WP2 | M2 UAT acceptance | 30% | 2027-10-31 | 2027 | 4836000 | 725400 | 5561400
Rollout | WP2 | M3 Go-live | 40% | 2027-11-30 | 2027 | 6448000 | 967200 | 7415200
Rollout | WP2 | M4 End of stabilisation | 10% | 2028-02-29 | 2028 | 1612000 | 241800 | 1853800
Rollout | WP3 | M1 Design & prototype sign-off | 20% | 2027-03-31 | 2027 | 3412600 | 511890 | 3924490
Rollout | WP3 | M2 UAT acceptance | 30% | 2027-10-31 | 2027 | 5118900 | 767835 | 5886735
Rollout | WP3 | M3 Go-live | 40% | 2027-11-30 | 2027 | 6825200 | 1023780 | 7848980
Rollout | WP3 | M4 End of stabilisation | 10% | 2028-02-29 | 2028 | 1706300 | 255945 | 1962245
Rollout | WP4 | M1 Design & prototype sign-off | 20% | 2028-05-31 | 2028 | 3467200 | 520080 | 3987280
Rollout | WP4 | M2 UAT acceptance | 30% | 2028-11-30 | 2028 | 5200800 | 780120 | 5980920
Rollout | WP4 | M3 Go-live | 40% | 2028-12-31 | 2028 | 6934400 | 1040160 | 7974560
Rollout | WP4 | M4 End of stabilisation | 10% | 2029-03-31 | 2029 | 1733600 | 260040 | 1993640
Rollout | WP5 | M1 Design & prototype sign-off | 20% | 2028-11-30 | 2028 | 3248200 | 487230 | 3735430
Rollout | WP5 | M2 UAT acceptance | 30% | 2029-05-31 | 2029 | 4872300 | 730845 | 5603145
Rollout | WP5 | M3 Go-live | 40% | 2029-06-30 | 2029 | 6496400 | 974460 | 7470860
Rollout | WP5 | M4 End of stabilisation | 10% | 2029-09-30 | 2029 | 1624100 | 243615 | 1867715
Rollout | WP6 | M1 Design & prototype sign-off | 20% | 2029-02-28 | 2029 | 3473400 | 521010 | 3994410
Rollout | WP6 | M2 UAT acceptance | 30% | 2029-08-31 | 2029 | 5210100 | 781515 | 5991615
Rollout | WP6 | M3 Go-live | 40% | 2029-09-30 | 2029 | 6946800 | 1042020 | 7988820
Rollout | WP6 | M4 End of stabilisation | 10% | 2029-12-31 | 2029 | 1736700 | 260505 | 1997205
Rollout | WP7 | M1 Design & prototype sign-off | 20% | 2029-05-31 | 2029 | 2706800 | 406020 | 3112820
Rollout | WP7 | M2 UAT acceptance | 30% | 2029-11-30 | 2029 | 4060200 | 609030 | 4669230
Rollout | WP7 | M3 Go-live | 40% | 2029-12-31 | 2029 | 5413600 | 812040 | 6225640
Rollout | WP7 | M4 End of stabilisation | 10% | 2030-03-31 | 2030 | 1353400 | 203010 | 1556410
Maintenance | MNT | Maintenance tranche 1 (3 months, 33 services) | 12.5% | 2030-03-31 | 2030 | 9405000 | 1410750 | 10815750
Maintenance | MNT | Maintenance tranche 2 (3 months, 33 services) | 12.5% | 2030-06-30 | 2030 | 9405000 | 1410750 | 10815750
Maintenance | MNT | Maintenance tranche 3 (3 months, 33 services) | 12.5% | 2030-09-30 | 2030 | 9405000 | 1410750 | 10815750
Maintenance | MNT | Maintenance tranche 4 (3 months, 33 services) | 12.5% | 2030-12-31 | 2030 | 9405000 | 1410750 | 10815750
Maintenance | MNT | Maintenance tranche 5 (3 months, 33 services) | 12.5% | 2031-03-31 | 2031 | 9405000 | 1410750 | 10815750
Maintenance | MNT | Maintenance tranche 6 (3 months, 33 services) | 12.5% | 2031-06-30 | 2031 | 9405000 | 1410750 | 10815750
Maintenance | MNT | Maintenance tranche 7 (3 months, 33 services) | 12.5% | 2031-09-30 | 2031 | 9405000 | 1410750 | 10815750
Maintenance | MNT | Maintenance tranche 8 (3 months, 33 services) | 12.5% | 2031-12-31 | 2031 | 9405000 | 1410750 | 10815750
|  | TOTAL |  |  |  | 186905000 | 28035750 | 214940750
|  | Rollout subtotal |  |  |  | 111665000
|  | Maintenance subtotal |  |  |  | 75240000
|  | Check: rollout payments = rollout total; maintenance = proposal |  |  |  | OK
|  | Check: each maintenance tranche within the cap |  |  |  | OK

## Original Offer
OrangeBD offer as submitted (Financial Proposal V4), for comparison
Source: BSTI 2.0 - Financial Proposal V4.pdf, pages 4–5. Inputs typed from the PDF; payments recomputed by formula.
Period | Year | Live services | Rate / service / month (BDT) | Months | Payment (BDT)
Aug–Dec 2026 | 2026 | 5 | 65000 | 5 | 1625000
Jan–Mar 2027 | 2027 | 5 | 180000 | 3 | 2700000
Apr–Jun 2027 | 2027 | 8 | 180000 | 3 | 4320000
Jul–Sep 2027 | 2027 | 11 | 180000 | 3 | 5940000
Oct–Dec 2027 | 2027 | 14 | 180000 | 3 | 7560000
Jan–Mar 2028 | 2028 | 17 | 155000 | 3 | 7905000
Apr–Jun 2028 | 2028 | 20 | 155000 | 3 | 9300000
Jul–Sep 2028 | 2028 | 23 | 155000 | 3 | 10695000
Oct–Dec 2028 | 2028 | 26 | 155000 | 3 | 12090000
Jan–Mar 2029 | 2029 | 29 | 130000 | 3 | 11310000
Apr–Jun 2029 | 2029 | 32 | 130000 | 3 | 12480000
Jul–Sep 2029 | 2029 | 33 | 130000 | 3 | 12870000
Oct–Dec 2029 | 2029 | 33 | 130000 | 3 | 12870000
2030 (maintenance) | 2030 | 33 | 95000 | 12 | 37620000
2031 (maintenance) | 2031 | 33 | 95000 | 12 | 37620000
Rollout total |  |  |  |  | 111665000
Maintenance total |  |  |  |  | 75240000
Grand total |  |  |  |  | 186905000
Check vs proposal (11,16,65,000 / 7,52,40,000) |  |  |  |  | OK

## Gantt
Development schedule (month by month)
D = design & prototype · B = build · U = UAT · G = go-live (deadline at month-end) · S = stabilisation / warranty. Driven by the schedule inputs on Packages.
Package | Scope | 2027-01-01 | 2027-02-01 | 2027-03-01 | 2027-04-01 | 2027-05-01 | 2027-06-01 | 2027-07-01 | 2027-08-01 | 2027-09-01 | 2027-10-01 | 2027-11-01 | 2027-12-01 | 2028-01-01 | 2028-02-01 | 2028-03-01 | 2028-04-01 | 2028-05-01 | 2028-06-01 | 2028-07-01 | 2028-08-01 | 2028-09-01 | 2028-10-01 | 2028-11-01 | 2028-12-01 | 2029-01-01 | 2029-02-01 | 2029-03-01 | 2029-04-01 | 2029-05-01 | 2029-06-01 | 2029-07-01 | 2029-08-01 | 2029-09-01 | 2029-10-01 | 2029-11-01 | 2029-12-01 | 2030-01-01 | 2030-02-01 | 2030-03-01
WP1 | BSTI 2.0 transformation: common platform, HRM & Leave, Payroll, Standards (BDS) sale; Accounts | D | B | B | B | U | G | S | S | S
WP2 | CM licence services (non-scope & scope: new, renewal, brand inclusion) + common suspension / cancellation / withdrawal |  |  | D | D | B | B | B | B | B | U | G | S | S | S
WP3 | Laboratory testing (Chemical, Physical, Energy Meter) and PCR services |  | D | D | B | B | B | B | B | B | U | G | S | S | S
WP4 | Enforcement & field metrology: Mobile Court, Surveillance, Verification, Tank Calibration, Metrology Licence, Storage Tank Calibration | [15 empty] | D | D | B | B | B | B | B | U | G | S | S | S
WP5 | MSC services (issue, renewal, scope inclusion) | [21 empty] | D | D | B | B | B | B | B | U | G | S | S | S
WP6 | Halal certification, LPG / Fuel station registration, Case Management | [24 empty] | D | D | B | B | B | B | B | U | G | S | S | S
WP7 | I&S Metrology Calibration (NML), Building measurement, BSW API integration, Importer/Exporter certificates* | [27 empty] | D | D | B | B | B | B | B | U | G | S | S | S
| Packages in parallel (design/build/UAT/go-live) | 1 | 2 | 3 | 3 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0

## Notes
Method, assumptions and points to confirm
Method
1 | The rollout total of BDT 11,16,65,000 (Financial Proposal V4, p.4) is kept unchanged. Only its split changes: from 'per live service per month' to 'per accepted deliverable'.
2 | BDT 16,25,000 for Aug–Dec 2026 is kept as a separate O&M package (WP0) because it pays for running the 5 live services, not new work. The remaining BDT 11,00,40,000 is allocated by work volume.
3 | Work volume = feature count per service from OrangeBD's own deck (BSTI 2.0.pptx, slides 14–46; 440 modules / 2,168 features in total). Where serial.docx splits one deck service into sub-types (Verification, Tank, Storage Tank, Surveillance), the parent's features are split equally.
4 | Features are weighted by work type: New = 1.0, Variant (renewal / brand / scope inclusion / re-certification) = 0.5, Live in v1 (re-platforming + migration) = 0.5. Session 1 found the variant SRS sections 85–99% identical. Factors are inputs; set all to 1.0 for a pure feature-count split.
5 | Packages follow serial.docx priority and are cut so that each approval, including 15% VAT, stays under BDT 2 crore. Change a row's package code on 'Work Volume' to move it; the cap check flags any breach.
6 | Payments are tied to accepted milestones (20% design sign-off / 30% UAT / 40% go-live / 10% after stabilisation), replacing monthly per-service billing. Each package price includes support of its services until maintenance starts in Jan 2030.
7 | Maintenance 2030–31 (BDT 7,52,40,000) is unchanged. Because a full year (3.76 crore) exceeds the cap, it is approved in quarterly tranches of BDT 94,05,000.
Development time limits
8 | Core services first: Accounts (WP1), CM (WP2), labs and PCR (WP3) go live by 30 Nov 2027, so they are fully running in December 2027 (user instruction). WP3 starts first (Feb 2027, 10 months) because CM scope, Halal and MSC all depend on lab testing; CM starts Mar 2027 (9 months) and integrates with the lab module. WP1–WP3 run in parallel Mar–Jun 2027.
9 | Approvals for WP1, WP3 and WP2 are needed one per month (by 30 Nov 2026, 31 Dec 2026 and 31 Jan 2027), each under 2 crore. WP4–WP7 follow from Apr 2028, staggered 3–6 months apart; final go-live 31 Dec 2029, the same end date as the proposal.
10 | Suggested contract clause (to confirm with the procurement / legal cell): liquidated damages for delay past the go-live deadline, e.g. 0.05% of the package value per day, capped at 10% (PPR and standard tender document terms apply).
BSTI estimates (yellow cells): no scope in the SRS or deck
11 | Common platform (unified portal and SSO, 23-office organogram, workflow / fee-payment / certificate-QR engines, v1 data migration): 60 features.
12 | BDS (Standards) sale re-platforming: 40 features. It is live in v1, has no SRS section, and takes service 23's slot.
13 | Suspension / cancellation / withdrawal of all certificates and licences (serial.docx footnote): 30 features, built once in WP2 and reused.
14 | MSC Scope Inclusion: 50 features. BSW API integration: 30 features.
Points to confirm
15 | Registered Importer/Exporter (new and renewal) are marked * in serial.docx. They are included as the last priority (WP7). Set 'Include?' to N on 'Work Volume' to drop them; the freed amount is spread over the rest automatically.
16 | Metrology dealer licence (earlier proposed as replacement for service 22) is not in serial.docx and is not costed here.
17 | VAT/tax rate for the approval check (15% assumed), and whether the 2-crore limit is measured including VAT.
18 | Feature counts are OrangeBD's own; they measure documented scope, not effort. An independent effort estimate would firm up the split.